## Bug_Tracking
Bug ID | Title | Module | Severity | Priority | Environment | Steps to Reproduce | Expected Result | Actual Result | Status | Assigned To | Reported By | Date
BUG-001 | Template selection from Templates page is not applied in the generator | Templates / Generator | High | High | Development | 1. Open /templates 2. Click any template card (e.g. Login) 3. Observe URL: /generator?template=<url-encoded JSON> 4. Check form fields and Generate button | Template steps/assertions loaded; Generate enabled | Generator ignores query param; form empty; Generate disabled; no template applied | Open | Dev Team | Errol Jay E DePaz | 2026-08-13
BUG-002 | Generated Playwright URL assertion is invalid JavaScript | Web (Playwright) Generator | Medium | Medium | Development | 1. Open /generator 2. Click Login template 3. Set Environment + Author 4. Click Generate Project 5. Inspect generated assertion: await expect(page).toHaveURL(/.*/dashboard.*/) | Valid URL assertion, e.g. await expect(page).toHaveURL(/.*dashboard.*/); | Malformed regex literal: unescaped '/' terminates regex early; code fails to parse | Open | Dev Team | Errol Jay E DePaz | 2026-08-13
BUG-003 | Settings: saved default framework is empty while UI shows Playwright | Settings | Low | Low | Development | 1. Open /settings 2. Click Save Settings without changing anything 3. Inspect localStorage.playgen_settings | Persisted value matches displayed selection (e.g. 'playwright') | UI shows 'Playwright' but saved defaultFramework is '' (empty) | Open | Dev Team | Errol Jay E DePaz | 2026-08-13
BUG-004 | JOIN Validation in SQL Builder generates plain SELECT instead of JOIN query | SQL Validation Studio | High | High | Development | 1. Open /sql-builder 2. Select 'JOIN Validation' 3. Enter table 'users' 4. Click Generate SQL | SQL query with JOIN clause between two tables | Generated SELECT * FROM users; - missing JOIN clause entirely | Open | Dev Team | Errol Jay E DePaz | 2026-08-13
BUG-005 | Mobile Appium templates crash Playwright generator with 'Generator not found' | Web (Playwright) Generator / Templates | High | High | Development | 1. Open /generator 2. Click 'Mobile Login (Appium)' template 3. Observe stats show 0 steps, editor shows 'Generator not found for playwright:Java' | Template generates valid Playwright code (JS/TS) | Mobile templates set language='Java' in Playwright generator; registry only has playwright:JavaScript/TypeScript; shows error message | Open | Dev Team | Errol Jay E DePaz | 2026-08-13
COV-001 | Dashboard card click-through not tested | Dashboard | Low | Low | Development | 1. Open /dashboard 2. Click each of the 6 tool cards | Each card navigates to its respective tool page | Not executed; card links verified in code only | Open | Dev Team | Errol Jay E DePaz | 2026-08-13
COV-002 | Logo link returns home - not tested | Navigation | Low | Low | Development | 1. From any page, click the PlayGen logo | Navigates to home page '/' | Not executed this pass | Open | Dev Team | Errol Jay E DePaz | 2026-08-13
COV-003 | Playwright Reset button not tested | Web (Playwright) Generator | Low | Low | Development | 1. Fill generator config 2. Click Reset | All config cleared; returns to template step | Not executed this pass | Open | Dev Team | Errol Jay E DePaz | 2026-08-13
COV-004 | Playwright Copy Code button not tested | Web (Playwright) Generator | Medium | Low | Development | 1. After generate, click Copy Code 2. Paste into text editor | Generated code copied to clipboard | Not executed (headless clipboard restrictions) | Open | Dev Team | Errol Jay E DePaz | 2026-08-13
COV-005 | Playwright Download button not tested | Web (Playwright) Generator | Medium | Low | Development | 1. After generate, click Download | File download starts | Not executed this pass | Open | Dev Team | Errol Jay E DePaz | 2026-08-13
COV-006 | Playwright TypeScript + POM generation not verified | Web (Playwright) Generator | Medium | Medium | Development | 1. Select TypeScript language 2. Select Page Object Model architecture 3. Load template 4. Generate | TypeScript POM project generated (.spec.ts, page objects, utils, config) | Not executed (Monaco editor content not readable after navigation) | Open | Dev Team | Errol Jay E DePaz | 2026-08-13
COV-007 | Selenium Python generation not tested | Web (Selenium) Generator | Medium | Low | Development | 1. Open /selenium-generator 2. Select Python 3. Select template 4. Generate | Python Selenium code generated | Not executed this pass | Open | Dev Team | Errol Jay E DePaz | 2026-08-13
COV-008 | Selenium JavaScript generation not tested | Web (Selenium) Generator | Medium | Low | Development | 1. Open /selenium-generator 2. Select JavaScript 3. Select template 4. Generate | JavaScript Selenium code generated | Not executed this pass | Open | Dev Team | Errol Jay E DePaz | 2026-08-13
COV-009 | Selenium C# generation not tested | Web (Selenium) Generator | Medium | Low | Development | 1. Open /selenium-generator 2. Select C# 3. Select template 4. Generate | C# Selenium code generated | Not executed this pass | Open | Dev Team | Errol Jay E DePaz | 2026-08-13
COV-010 | Appium Python generation not tested | Mobile (Appium) Generator | Medium | Low | Development | 1. Open /appium-generator 2. Select Python 3. Select template 4. Generate | Python Appium code generated | Not executed this pass | Open | Dev Team | Errol Jay E DePaz | 2026-08-13
COV-011 | Appium JavaScript generation not tested | Mobile (Appium) Generator | Medium | Low | Development | 1. Open /appium-generator 2. Select JavaScript 3. Select template 4. Generate | JavaScript Appium code generated | Not executed this pass | Open | Dev Team | Errol Jay E DePaz | 2026-08-13
COV-012 | Appium C# generation not tested | Mobile (Appium) Generator | Medium | Low | Development | 1. Open /appium-generator 2. Select C# 3. Select template 4. Generate | C# Appium code generated | Not executed this pass | Open | Dev Team | Errol Jay E DePaz | 2026-08-13
COV-013 | CI/CD Selenium + Java + Jenkins pipeline not tested | CI/CD Generator | Medium | Low | Development | 1. Open /cicd-generator 2. Select Selenium, Java, Jenkins 3. Configure steps 4-6 4. Generate | Valid Jenkinsfile generated | Not executed this pass | Open | Dev Team | Errol Jay E DePaz | 2026-08-13
COV-014 | CI/CD Appium + Azure DevOps pipeline not tested | CI/CD Generator | Medium | Low | Development | 1. Open /cicd-generator 2. Select Appium, Azure DevOps 3. Configure steps 4-6 4. Generate | Valid Azure DevOps YAML generated | Not executed this pass | Open | Dev Team | Errol Jay E DePaz | 2026-08-13
COV-015 | CI/CD Advanced Options expand not tested | CI/CD Generator | Low | Low | Development | 1. Open /cicd-generator 2. Click 'Show Advanced Options' | Advanced options section expands | Not executed this pass | Open | Dev Team | Errol Jay E DePaz | 2026-08-13
COV-016 | Settings Reset to Defaults not tested | Settings | Low | Low | Development | 1. Open /settings 2. Change any setting 3. Click 'Reset to Defaults' | Settings revert to default values | Not executed this pass | Open | Dev Team | Errol Jay E DePaz | 2026-08-13
COV-017 | SQL Builder Custom SELECT Query not tested | SQL Validation Studio | Medium | Low | Development | 1. Open /sql-builder 2. Select 'Custom SELECT Query' 3. Enter custom query 4. Click Generate | Custom query accepted and displayed in output | Not executed this pass | Open | Dev Team | Errol Jay E DePaz | 2026-08-13